## Sheet1
Task | Website template | Build database to store admin's details | Admin login | Build database to store recipe | CRUD Recipe | Extract data from database for admin & recipe | Testing & Refactoring | Actual Remaining Hours | Estimated Remaining Hours
Total Hours | 13 | 9 | 8 | 17 | 19 | 13 | 9 | 88 | 88
Hours Spent on Day15,14 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 70.4
Hours Spent on Day13,12,11 | 0 | 9 | 8 | 0 | 0 | 0 | 2 | 56 | 52.8
Hours Spent on Day10,9,8,7 | 0 | 0 | 0 | 8 | 10 | 0 | 2 | 36 | 35.2
Hours Spent on Day6,5,4 | 0 | 0 | 0 | 9 | 9 | 0 | 2 | 16 | 17.6
Hours Spent on Day3,2,1 | 0 | 0 | 0 | 0 | 0 | 13 | 3 | 0 | 0
Sprint Review